## Gantt
Construction schedule
| Project start | 2026-11-02
Free template by Planitude · planitude.app
WBS | Task | Start | Duration (working days) | Finish | Predecessors | % complete | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | 2027-05-10 | 2027-05-17 | 2027-05-24 | 2027-05-31
1 | Pre-construction | 2026-11-02 | 35 | 2026-12-18 |  | 0%
1.1 | Detailed design | 2026-11-02 | 15 | 2026-11-20 |  | 0%
1.2 | Building permit | 2026-11-23 | 20 | 2026-12-18 | 1.1 | 0%
1.3 | Tender and construction contract | 2026-11-23 | 10 | 2026-12-04 | 1.1 | 0%
1.4 | Start of works | 2026-12-18 | 0 | 2026-12-18 | 1.2; 1.3 | 0%
2 | Site setup and earthworks | 2026-12-21 | 11 | 2027-01-04 |  | 0%
2.1 | Site setup | 2026-12-21 | 3 | 2026-12-23 | 1.4 | 0%
2.2 | Excavation and earthworks | 2026-12-24 | 8 | 2027-01-04 | 2.1 | 0%
3 | Structure | 2027-01-05 | 37 | 2027-02-24 |  | 0%
3.1 | Foundations | 2027-01-05 | 12 | 2027-01-20 | 2.2 | 0%
3.2 | Superstructure: columns, walls and beams | 2027-01-21 | 25 | 2027-02-24 | 3.1 | 0%
3.3 | Floor slabs and roof | 2027-02-04 | 15 | 2027-02-24 | 3.2SS+10 | 0%
3.4 | Structure topped out | 2027-02-24 | 0 | 2027-02-24 | 3.2; 3.3 | 0%
4 | Building envelope | 2027-02-25 | 21 | 2027-03-25 |  | 0%
4.1 | Masonry and infill walls | 2027-02-25 | 15 | 2027-03-17 | 3.4 | 0%
4.2 | Waterproofing and insulation | 2027-02-25 | 8 | 2027-03-08 | 3.4 | 0%
4.3 | External windows and doors | 2027-03-18 | 6 | 2027-03-25 | 4.1 | 0%
5 | Building services (MEP) | 2027-03-18 | 15 | 2027-04-07 |  | 0%
5.1 | Plumbing and heating | 2027-03-18 | 15 | 2027-04-07 | 4.1 | 0%
5.2 | Electrical installation | 2027-03-18 | 12 | 2027-04-02 | 4.1 | 0%
6 | Finishes | 2027-03-26 | 37 | 2027-05-17 |  | 0%
6.1 | Plastering and screeds | 2027-04-08 | 10 | 2027-04-21 | 5.1; 5.2 | 0%
6.2 | Flooring and tiling | 2027-04-22 | 12 | 2027-05-07 | 6.1 | 0%
6.3 | Painting and decorating | 2027-05-10 | 6 | 2027-05-17 | 6.2 | 0%
6.4 | External works and landscaping | 2027-03-26 | 8 | 2027-04-06 | 4.3; 4.2 | 0%
7 | Inspection and handover | 2027-05-18 | 5 | 2027-05-24 |  | 0%
7.1 | Testing, commissioning and certificates | 2027-05-18 | 5 | 2027-05-24 | 6.3; 6.4 | 0%
7.2 | Practical completion and handover | 2027-05-24 | 0 | 2027-05-24 | 7.1 | 0%

## Instructions
Construction schedule
1. Type the project start date in cell C2: every date in the plan moves with it.
2. Change a duration in column D: the finish date and the tasks that depend on it are recalculated, skipping Saturdays and Sundays.
3. The Predecessors column lists the WBS codes of the tasks each row depends on (SS = start-to-start, +10 = lag in working days).
4. The bars on the right are drawn by conditional formatting, one column per week: blue for tasks, dark for phases, gold for milestones.
5. When you add a row, copy the formulas from the row above and update the references to its predecessors.
Free template by Planitude · planitude.app