## Slide 1
Event planning
Phases and milestones · Nov 2, 2026 – Dec 18, 2026
Nov
Dec
Free template by Planitude · planitude.app
Planning
Suppliers
Promotion
Event

## Slide 2
Event planning
Tasks · Nov 2, 2026 – Dec 18, 2026
Nov
Dec
Free template by Planitude · planitude.app
1 Planning
1.1 Goals and budget
1.2 Choose date and venue
1.3 Venue booked
1.4 Program and speakers
2 Suppliers
2.1 Catering
2.2 AV and staging
2.3 Guest and speaker accommodation
3 Promotion
3.1 Event page and registration
3.2 Invitations
3.3 Promotion campaign
4 Event

## Slide 3
Event planning
Tasks · Nov 2, 2026 – Dec 18, 2026
Nov
Dec
Free template by Planitude · planitude.app
4.1 Final program
4.2 Rehearsal and staff briefing
4.3 Event day
4.4 Thank-you notes and survey
4.5 Budget review and final report