## Gantt
Event planning
| Project start | 2026-11-02
Free template by Planitude · planitude.app
WBS | Task | Start | Duration (working days) | Finish | Predecessors | % complete | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21
1 | Planning | 2026-11-02 | 12 | 2026-11-17 |  | 0%
1.1 | Goals and budget | 2026-11-02 | 2 | 2026-11-03 |  | 0%
1.2 | Choose date and venue | 2026-11-04 | 5 | 2026-11-10 | 1.1 | 0%
1.3 | Venue booked | 2026-11-10 | 0 | 2026-11-10 | 1.2 | 0%
1.4 | Program and speakers | 2026-11-04 | 10 | 2026-11-17 | 1.1 | 0%
2 | Suppliers | 2026-11-11 | 3 | 2026-11-13 |  | 0%
2.1 | Catering | 2026-11-11 | 3 | 2026-11-13 | 1.3 | 0%
2.2 | AV and staging | 2026-11-11 | 3 | 2026-11-13 | 1.3 | 0%
2.3 | Guest and speaker accommodation | 2026-11-11 | 3 | 2026-11-13 | 1.3 | 0%
3 | Promotion | 2026-11-11 | 22 | 2026-12-10 |  | 0%
3.1 | Event page and registration | 2026-11-11 | 5 | 2026-11-17 | 1.3 | 0%
3.2 | Invitations | 2026-11-18 | 2 | 2026-11-19 | 3.1 | 0%
3.3 | Promotion campaign | 2026-11-20 | 15 | 2026-12-10 | 3.2 | 0%
4 | Event | 2026-12-04 | 11 | 2026-12-18 |  | 0%
4.1 | Final program | 2026-12-04 | 2 | 2026-12-07 | 1.4; 3.3SS+10 | 0%
4.2 | Rehearsal and staff briefing | 2026-12-11 | 1 | 2026-12-11 | 4.1; 2.1; 2.2; 2.3; 3.3 | 0%
4.3 | Event day | 2026-12-11 | 0 | 2026-12-11 | 4.2 | 0%
4.4 | Thank-you notes and survey | 2026-12-14 | 2 | 2026-12-15 | 4.3 | 0%
4.5 | Budget review and final report | 2026-12-16 | 3 | 2026-12-18 | 4.4 | 0%

## Instructions
Event planning
1. Type the project start date in cell C2: every date in the plan moves with it.
2. Change a duration in column D: the finish date and the tasks that depend on it are recalculated, skipping Saturdays and Sundays.
3. The Predecessors column lists the WBS codes of the tasks each row depends on (SS = start-to-start, +10 = lag in working days).
4. The bars on the right are drawn by conditional formatting, one column per week: blue for tasks, dark for phases, gold for milestones.
5. When you add a row, copy the formulas from the row above and update the references to its predecessors.
Free template by Planitude · planitude.app