## Gantt
Home renovation
| Project start | 2026-11-02
Free template by Planitude · planitude.app
WBS | Task | Start | Duration (working days) | Finish | Predecessors | % complete | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01
1 | Design | 2026-11-02 | 27 | 2026-12-08 |  | 0%
1.1 | Survey and measurements | 2026-11-02 | 2 | 2026-11-03 |  | 0%
1.2 | Interior design | 2026-11-04 | 10 | 2026-11-17 | 1.1 | 0%
1.3 | Permits and paperwork | 2026-11-18 | 15 | 2026-12-08 | 1.2 | 0%
1.4 | Contractor quotes | 2026-11-18 | 10 | 2026-12-01 | 1.2 | 0%
1.5 | Contractor chosen | 2026-12-01 | 0 | 2026-12-01 | 1.4 | 0%
2 | Demolition | 2026-12-09 | 8 | 2026-12-18 |  | 0%
2.1 | Site setup | 2026-12-09 | 1 | 2026-12-09 | 1.3; 1.5 | 0%
2.2 | Demolition and strip-out | 2026-12-10 | 5 | 2026-12-16 | 2.1 | 0%
2.3 | Debris removal | 2026-12-17 | 2 | 2026-12-18 | 2.2 | 0%
3 | Systems | 2026-12-21 | 11 | 2027-01-04 |  | 0%
3.1 | Plumbing | 2026-12-21 | 6 | 2026-12-28 | 2.3 | 0%
3.2 | Electrical | 2026-12-21 | 6 | 2026-12-28 | 2.3 | 0%
3.3 | Screeds and plastering | 2026-12-29 | 5 | 2027-01-04 | 3.1; 3.2 | 0%
4 | Finishes | 2027-01-05 | 13 | 2027-01-21 |  | 0%
4.1 | Flooring and tiling | 2027-01-05 | 8 | 2027-01-14 | 3.3 | 0%
4.2 | Doors and windows | 2027-01-05 | 3 | 2027-01-07 | 3.3 | 0%
4.3 | Painting | 2027-01-15 | 5 | 2027-01-21 | 4.1 | 0%
4.4 | Kitchen and bathroom fixtures | 2027-01-15 | 4 | 2027-01-20 | 4.1 | 0%
5 | Handover | 2027-01-22 | 2 | 2027-01-25 |  | 0%
5.1 | Final cleaning | 2027-01-22 | 2 | 2027-01-25 | 4.3; 4.4; 4.2 | 0%
5.2 | Final inspection and handover | 2027-01-25 | 0 | 2027-01-25 | 5.1 | 0%

## Instructions
Home renovation
1. Type the project start date in cell C2: every date in the plan moves with it.
2. Change a duration in column D: the finish date and the tasks that depend on it are recalculated, skipping Saturdays and Sundays.
3. The Predecessors column lists the WBS codes of the tasks each row depends on (SS = start-to-start, +10 = lag in working days).
4. The bars on the right are drawn by conditional formatting, one column per week: blue for tasks, dark for phases, gold for milestones.
5. When you add a row, copy the formulas from the row above and update the references to its predecessors.
Free template by Planitude · planitude.app