## Gantt
Marketing campaign
| Project start | 2026-11-02
Free template by Planitude · planitude.app
WBS | Task | Start | Duration (working days) | Finish | Predecessors | % complete | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04
1 | Strategy | 2026-11-02 | 9 | 2026-11-12 |  | 0%
1.1 | Goals and KPIs | 2026-11-02 | 2 | 2026-11-03 |  | 0%
1.2 | Audience research | 2026-11-04 | 3 | 2026-11-06 | 1.1 | 0%
1.3 | Budget and channels | 2026-11-09 | 2 | 2026-11-10 | 1.2 | 0%
1.4 | Creative brief | 2026-11-11 | 2 | 2026-11-12 | 1.3 | 0%
2 | Production | 2026-11-13 | 7 | 2026-11-23 |  | 0%
2.1 | Copywriting | 2026-11-13 | 5 | 2026-11-19 | 1.4 | 0%
2.2 | Visuals and video | 2026-11-13 | 7 | 2026-11-23 | 1.4 | 0%
2.3 | Landing page | 2026-11-13 | 5 | 2026-11-19 | 1.4 | 0%
2.4 | Creative approved | 2026-11-23 | 0 | 2026-11-23 | 2.1; 2.2; 2.3 | 0%
3 | Go-live | 2026-11-24 | 22 | 2026-12-23 |  | 0%
3.1 | Campaign and tracking setup | 2026-11-24 | 2 | 2026-11-25 | 2.4 | 0%
3.2 | Campaign live | 2026-11-25 | 0 | 2026-11-25 | 3.1 | 0%
3.3 | Monitor and optimize | 2026-11-26 | 20 | 2026-12-23 | 3.2 | 0%
3.4 | Mid-campaign report | 2026-12-10 | 1 | 2026-12-10 | 3.3SS+10 | 0%
4 | Analysis | 2026-12-24 | 3 | 2026-12-28 |  | 0%
4.1 | Final report and lessons learned | 2026-12-24 | 3 | 2026-12-28 | 3.3 | 0%

## Instructions
Marketing campaign
1. Type the project start date in cell C2: every date in the plan moves with it.
2. Change a duration in column D: the finish date and the tasks that depend on it are recalculated, skipping Saturdays and Sundays.
3. The Predecessors column lists the WBS codes of the tasks each row depends on (SS = start-to-start, +10 = lag in working days).
4. The bars on the right are drawn by conditional formatting, one column per week: blue for tasks, dark for phases, gold for milestones.
5. When you add a row, copy the formulas from the row above and update the references to its predecessors.
Free template by Planitude · planitude.app