## Gantt
Store opening
| Project start | 2026-11-02
Free template by Planitude · planitude.app
WBS | Task | Start | Duration (working days) | Finish | Predecessors | % complete | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08
1 | Planning | 2026-11-02 | 45 | 2027-01-01 |  | 0%
1.1 | Business plan | 2026-11-02 | 10 | 2026-11-13 |  | 0%
1.2 | Find the premises | 2026-11-16 | 15 | 2026-12-04 | 1.1 | 0%
1.3 | Lease signed | 2026-12-04 | 0 | 2026-12-04 | 1.2 | 0%
1.4 | Licenses and permits | 2026-12-07 | 20 | 2027-01-01 | 1.3 | 0%
2 | Fit-out | 2026-12-07 | 33 | 2027-01-20 |  | 0%
2.1 | Store design | 2026-12-07 | 10 | 2026-12-18 | 1.3 | 0%
2.2 | Fit-out works | 2026-12-21 | 20 | 2027-01-15 | 2.1 | 0%
2.3 | Signage and windows | 2026-12-21 | 5 | 2026-12-25 | 2.1 | 0%
2.4 | POS and IT systems | 2027-01-18 | 3 | 2027-01-20 | 2.2 | 0%
3 | Stock and staff | 2026-12-07 | 38 | 2027-01-27 |  | 0%
3.1 | Suppliers and first order | 2026-12-07 | 10 | 2026-12-18 | 1.3 | 0%
3.2 | Hire staff | 2026-12-07 | 15 | 2026-12-25 | 1.3 | 0%
3.3 | Staff training | 2027-01-21 | 5 | 2027-01-27 | 3.2; 2.4 | 0%
3.4 | Stock delivery and display | 2027-01-18 | 3 | 2027-01-20 | 2.2; 3.1 | 0%
4 | Opening | 2027-01-27 | 6 | 2027-02-03 |  | 0%
4.1 | Soft opening | 2027-01-27 | 0 | 2027-01-27 | 3.3; 3.4; 1.4; 2.3 | 0%
4.2 | Opening promotion | 2027-01-28 | 5 | 2027-02-03 | 4.1 | 0%
4.3 | Grand opening | 2027-02-03 | 0 | 2027-02-03 | 4.2 | 0%

## Instructions
Store opening
1. Type the project start date in cell C2: every date in the plan moves with it.
2. Change a duration in column D: the finish date and the tasks that depend on it are recalculated, skipping Saturdays and Sundays.
3. The Predecessors column lists the WBS codes of the tasks each row depends on (SS = start-to-start, +10 = lag in working days).
4. The bars on the right are drawn by conditional formatting, one column per week: blue for tasks, dark for phases, gold for milestones.
5. When you add a row, copy the formulas from the row above and update the references to its predecessors.
Free template by Planitude · planitude.app