## Gantt
Thesis or research project
| Project start | 2026-11-02
Free template by Planitude · planitude.app
WBS | Task | Start | Duration (working days) | Finish | Predecessors | % complete | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15
1 | Proposal | 2026-11-02 | 25 | 2026-12-04 |  | 0%
1.1 | Choose the topic | 2026-11-02 | 5 | 2026-11-06 |  | 0%
1.2 | Literature review | 2026-11-09 | 15 | 2026-11-27 | 1.1 | 0%
1.3 | Write the proposal | 2026-11-30 | 5 | 2026-12-04 | 1.2 | 0%
1.4 | Proposal approved | 2026-12-04 | 0 | 2026-12-04 | 1.3 | 0%
2 | Research | 2026-12-07 | 35 | 2027-01-22 |  | 0%
2.1 | Methodology design | 2026-12-07 | 5 | 2026-12-11 | 1.4 | 0%
2.2 | Data collection | 2026-12-14 | 20 | 2027-01-08 | 2.1 | 0%
2.3 | Data analysis | 2027-01-11 | 10 | 2027-01-22 | 2.2 | 0%
3 | Writing | 2026-12-07 | 63 | 2027-03-03 |  | 0%
3.1 | Introduction and literature chapter | 2026-12-07 | 10 | 2026-12-18 | 1.4 | 0%
3.2 | Methods chapter | 2026-12-14 | 5 | 2026-12-18 | 2.1 | 0%
3.3 | Results chapter | 2027-01-25 | 8 | 2027-02-03 | 2.3 | 0%
3.4 | Discussion and conclusions | 2027-02-04 | 7 | 2027-02-12 | 3.3; 3.1 | 0%
3.5 | Revision with the supervisor | 2027-02-15 | 10 | 2027-02-26 | 3.4; 3.2 | 0%
3.6 | Formatting and bibliography | 2027-03-01 | 3 | 2027-03-03 | 3.5 | 0%
4 | Defense | 2027-03-03 | 6 | 2027-03-10 |  | 0%
4.1 | Thesis submitted | 2027-03-03 | 0 | 2027-03-03 | 3.6 | 0%
4.2 | Prepare the presentation | 2027-03-04 | 5 | 2027-03-10 | 4.1 | 0%
4.3 | Thesis defense | 2027-03-10 | 0 | 2027-03-10 | 4.2 | 0%

## Instructions
Thesis or research project
1. Type the project start date in cell C2: every date in the plan moves with it.
2. Change a duration in column D: the finish date and the tasks that depend on it are recalculated, skipping Saturdays and Sundays.
3. The Predecessors column lists the WBS codes of the tasks each row depends on (SS = start-to-start, +10 = lag in working days).
4. The bars on the right are drawn by conditional formatting, one column per week: blue for tasks, dark for phases, gold for milestones.
5. When you add a row, copy the formulas from the row above and update the references to its predecessors.
Free template by Planitude · planitude.app