## Gantt
Wedding
| Project start | 2026-11-02
Free template by Planitude · planitude.app
WBS | Task | Start | Duration (working days) | Finish | Predecessors | % complete | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01
1 | The basics | 2026-11-02 | 12 | 2026-11-17 |  | 0%
1.1 | Budget and guest list | 2026-11-02 | 5 | 2026-11-06 |  | 0%
1.2 | Choose the date | 2026-11-09 | 2 | 2026-11-10 | 1.1 | 0%
1.3 | Book the venue | 2026-11-11 | 3 | 2026-11-13 | 1.2 | 0%
1.4 | Ceremony and paperwork | 2026-11-11 | 5 | 2026-11-17 | 1.2 | 0%
2 | Suppliers | 2026-11-11 | 30 | 2026-12-22 |  | 0%
2.1 | Photographer and video | 2026-11-16 | 5 | 2026-11-20 | 1.3 | 0%
2.2 | Catering and menu | 2026-11-16 | 10 | 2026-11-27 | 1.3 | 0%
2.3 | Music | 2026-11-16 | 5 | 2026-11-20 | 1.3 | 0%
2.4 | Flowers and decor | 2026-11-16 | 5 | 2026-11-20 | 1.3 | 0%
2.5 | Wedding attire | 2026-11-11 | 30 | 2026-12-22 | 1.2 | 0%
3 | Invitations | 2026-11-16 | 48 | 2027-01-20 |  | 0%
3.1 | Save the date | 2026-11-16 | 3 | 2026-11-18 | 1.3 | 0%
3.2 | Send invitations | 2026-12-17 | 5 | 2026-12-23 | 3.1FS+20 | 0%
3.3 | Collect RSVPs | 2026-12-24 | 20 | 2027-01-20 | 3.2 | 0%
4 | Final details | 2027-01-21 | 7 | 2027-01-29 |  | 0%
4.1 | Seating plan | 2027-01-21 | 3 | 2027-01-25 | 3.3 | 0%
4.2 | Final supplier meetings | 2027-01-26 | 3 | 2027-01-28 | 4.1; 2.1; 2.2; 2.3; 2.4 | 0%
4.3 | Ceremony rehearsal | 2027-01-29 | 1 | 2027-01-29 | 4.2; 1.4 | 0%
4.4 | The big day | 2027-01-29 | 0 | 2027-01-29 | 4.3; 2.5 | 0%

## Instructions
Wedding
1. Type the project start date in cell C2: every date in the plan moves with it.
2. Change a duration in column D: the finish date and the tasks that depend on it are recalculated, skipping Saturdays and Sundays.
3. The Predecessors column lists the WBS codes of the tasks each row depends on (SS = start-to-start, +10 = lag in working days).
4. The bars on the right are drawn by conditional formatting, one column per week: blue for tasks, dark for phases, gold for milestones.
5. When you add a row, copy the formulas from the row above and update the references to its predecessors.
Free template by Planitude · planitude.app